## Slide 1
Eurazeo AI Hackathon
Refined Proposal — February 2026
Accelerating AI adoption across the Eurazeo portfolio through a hands-on, product-led build sprint.
Prepared by Yelin.io • Confidential

## Slide 2
Why This Hackathon & Why Now
PRIMARY
Surface real AI use cases ready for deployment within 24 hours
SECONDARY
Build cross-portfolio community and shared AI playbook
ADDITIONAL
Generate LP-facing proof of AI value creation across the portfolio
Sprint learning > slow pilots — move from exploration to production in one weekend.

## Slide 3
Event Format & Product Focus
FORMAT
24-Hour Build Sprint
Teams of 3–7 people
Cross-functional: product, engineering, ops
Time-boxed AI coaching sessions
Scale: 20–30 companies, ~5 per company
Plan for ~60% attendance
PRODUCT-LED APPROACH
Focus on real product roadmap items
Challenges tied to actual business problems
Product-led org best practices baked in
Outputs: working prototypes, not slide decks
Stronger sales language: AI as accelerator
Target: May 2026 — October is too far out. Move fast while momentum is high.

## Slide 4
Budget & Logistics
GOLD
€120k
Full-scale: 30 companies
Top-tier venue + catering
Industry Expert speakers
Live-streamed event
Comprehensive swag + prizes
SILVER
€65k
Mid-scale: 20–25 companies
Quality venue + catering
Industry expert speakers
Professional recording
Selective swag + prizes
LEAN
€40k
Focused: 15–20 companies
Eurazeo offices (no venue cost)
Internal + partner mentors
Photo/video highlights
Essential prizes only
Venue: Eurazeo offices (no cost) • Partners provide AI credits • Judging panel: Eurazeo VIPs + partners

## Slide 5
Timeline & Decisions Needed
WK 1–2
Lock budget tier
& confirm scope
WK 3–4
Partner outreach
& AI credits secured
WK 5–6
Company invitations
& challenge design
WK 7–8
Final logistics
& dry run
DECISIONS NEEDED NOW
Which budget tier? Gold / Silver / Lean
Confirm May 2026 target date
Approve partner outreach list (AI vendors, cloud providers)
Define Yelin.io scope: full production or advisory?
Identify Eurazeo VIPs + partners for judging panel